## Hoja1
Module	Test Case	Result	Observations	Screenshot
User Registration	TS_GUI_UR_01	Passed with observations	Error messages should be visible, they overlap with the other fields
			Error message should include that pass will need special characters

Login	TS_GUI_L_01	Passed with observation	Error messages should be visible, they overlap with the other fields

Profile Information	TS_GUI_PI_01	Passed

Edit Profile	TS_GUI_EP_01	Failed	Error message is not “You can’t leave this blank”
	TS_GUI_EP_03	Passed

Create Project	TS_GUI_PC_01	Passed

User Project Mapping	TS_UPM_01	Passed

Project Setup	TS_GUI_PS_08	Passed
	TS_GUI_PS_19	Passed
	TS_GUI_PS_15	Passed with observations	Leaving user name field blank and then try to add there is no error or message

Member Management	TS_GUI_MM_01	Passed with observations	No error messages when trying to enter a member without role
			It would be nice if members edits-upates refresh automatically in the page, as adding sprint

Sprint Administration	TS_GUI_SPA_03	Failed	When there is no next sprint, the app should validate and send a warning that there is no next print to place the stories and tha the stories not closed will be lost
	TS_GUI_SPA_05	Passed
	TS_GUI_SPA_08	Passed

Stories Administration	TS_GUI_STA_01	Passed
	TS_GUI_STA_03	Passed

Board Page Movements	All	Passed

User Deletion	TS_UD_01	Passed
	TS_UD_02	Passed